# Project Meeting minutes

| Date: 23.04 – 25.04. Author: Ioana Capatu Chair: Bildungsdirektion Vorarlberg PH NÖ In Attendance: PH NÖ: Carmen Sippl, Ioana Capatu, Rita Krebs ELTE: Gabriella Perge Siegen: Berbeli Wanning, Jana Mikota LMU: Christian Hoiss Maribor: Jana Ambrožič-Dolinšek, Alja Lipavic Oštir Tartu: Emanuele Bardone, Liisi Pajula EKUZ: Sabine Seidler BD Vorarlberg: Ivo Walser, Christoph Rinderer DROSTE: Friederike Krüger, Cilly Krämer Other: |  |  |
| --- | --- | --- |
| Meeting refers to: x Project Management x TNP x Multiplier Event x Dissemination x WP1 CNL Manual Part 1 x WP1 CNL Manual Part 2 x WP2 CNL Platform x WP2 CNL Learning Scenarios x WP3 CNL MOOC x WP4 CNL Narratives  Other:  Select one |  |  |
| To-do list from last meeting: Action Items/Responsible Person | Status | Due |
| Learning scenario of the month | ongoing |  |
| CNL News & Dissemination Database | ongoing |  |
| Comments to to-do list form last meeting: |  |  |
| Minutes: |  |  |
| 23.04.: Dissemination Strategy WP1:  Berbeli reported extensive dissemination activities. She noted that WP1's visibility increased significantly once WP2 was also launched. The co-working between the two work packages proved highly beneficial for practitioners: - Teachers often engage first with either the Learning Scenarios (WP2) or the Handbook (WP1), which leads them to explore the other component as well. - The real success lies in promoting both work packages together rather than separately.  Emanuele shared that he integrated the Learning Scenarios into his courses and mentioned the MOOC and Handbook.  Jana: Her students are using the Handbook as a basis for their master's theses.  Christian: Reported similar positive experiences; students were pleased to have access to the materials. Dissemination idea: Contact federal teacher training centers.  Carmen: Students selected individual chapters from the Handbook to develop their own Learning Scenarios.  Ioana: Suggested asking teachers we know to write short blog-style reflections about their experience with the Learning Scenarios.  Alja: Is planning exercises based on the scenarios for her own subjects; she also published a scientific article related to the project. Jana is planning a publication as well.  Gabriella: Disseminated through various platforms and conferences. A new group in Foreign Language Didactics is working with the Learning Scenarios, particularly focusing on sustainability ("Konferenz der Tiere").  Carmen emphasized that Part 2 of the manual should not be forgotten and suggested creating an interactive web dialogue for it.  Berbeli and Carmen present after the meeting CNL to the Stakeholders Meeting Dissemination Strategy WP2: - Christian Hoiß: Emphasized the need to strategically approach teacher training centers, schools, and ministries. Important to reach structural levels for broader impact. - Berbeli:Will present the project at the German Rectors’ Conference (Hochschulrektorenkonferenz). "DER DEUTSCHUNTERRICHT" (Issue 3/25, June) for dissemination, a widely read journal among teachers, will have a special issue ppublished about CNL. Important: - R&E-Source is now published!! Make sure it is linked on project websites. 24.04.: Project Management updates (See more on the slides attached to this mail):  Milestones: - WP1–WP3 are completed. - WP4 focuses on publication and is on track. - The project is within its timeframe.  Dissemination Strategy: - All partners should continue communicating results actively. - Every dissemination activity counts and should be documented.  Final Report Preparation: - Consider how the project will be disseminated after completion (e.g., website remaining accessible). - Partners must contribute to the final report, ensuring completeness of documentation.  Action Items: - Dissemination database: Minimum of 8 activities per partner per year. - Check and complete all files on the intranet. - Upload all travel documents. - Start drafting the final report in September. - Provide national agency access to the intranet before October.  Next Quality Board Meeting: - Scheduled for 2 July. - Timesheets must be sent to Rita by 1 October 2025. Dissemination Strategy WP 3:  Integration of the CNL-GPT and the MOOC into existing university courses: - The MOOC could be added to the official course list at University of Tartu. - Credit points for the MOOC might be possible but will require administrative work.  Dissemination through: - Articles, conference talks, events. - Planned integration into two Master’s courses  Other dissemination activities: - Emanuele and Liisi are referencing CNL in their new project. - Sabine will use CNL as a reference at the next Forum Anthropocene (focus: National Parks and Sustainability). WP 4:  Reader to be finalized by the end of May.  Introduced featured authors: - Melanie Laibl, Lilya Burdinskaya, Milena Michiko Flasar, Martin Pollack, and Natalja Klutscharjowa.  Multilingual translations: - 209 pages of stories available in English, Estonian, French, Romanian, Russian, Slovenian, Ukrainian, and Hungarian.  Reader will be published in open access.  Feedback request: - All partners are asked to review the “CNL Instruction Manual” accompanying the reader. Positive feedback overall. Sabine asked for clarification on terminology ("more-than-human" and whether to use "environmental and climate crisis" instead of "environmental crisis and climate change"). 25.04.: Final Report:  Everyone must contribute actively!  Important: Provide 1–2 sentences answering relevance questions from everyone.  Presentation slides will be shared.  Questions discussed openly. Regular meetings scheduled: - 23 May, 27 June, 14 August (note: 15 August is a holiday), and 19 September always at 16:30.  Next Quality Board meeting: 2 July. TNP & MP in Baden: Hotel information for October meeting: - Dates: 21–23 October - Venue: At the Park Hotel, Baden - Reservation keyword: "PH NÖ Kongress" - Hotel Website  Reminder: - Book rooms soon; limited availability.  Jana suggested: - The program should note that keynote speeches will be held in German but slides will be in English.  Invitation to final event: - Partners should distribute the invitation widely (attached in the mail). |  |  |
| To-do list: | Responsible person | Due |
| Learning scenario of the month | all |  |
| CNL News & Dissemination Database | all |  |
| Link R&E-Source to your websites | all |  |
| Time-sheets | all | 01.10.25 |
| Final Report | all | 30.06.25 |
| Comments to to-do list: |  |  |
| Miscellaneous: |  |  |